## Tabelle1
Datum | Starttijd | Eindtijd | Bezigheden
2022-08-24 | 10:00 | 13:00 | Intro conversation with Jeroen Veen
2022-08-29 | 9:00 | 14:00 | kickoff + worked on POA
2022-08-30 | 9:15 | 15:00 | Worked on POA, conversation with jeroen about product functionality, details
2022-08-31 | 11:00 | 16:00 | Worked on global design, kesselring methode, conversation jeroen about global design.
2022-09-01 | 9:00 | 17:00 | Pros and cons list created. State diagram created. Systeem architectuur enhanced after conversation with jeroen
2022-09-02 | 10:00 | 16:30 | Worked on schematic for led, tested led, read datasheet led and led-driver
2022-09-05 | 9:00 | 16:00 | Worked on schematic for led with new chip, solderd cn5711 driver for led for testing, back-upped old and created fresh raspberry pi image. Wrote hardware pwm code python for cn5711 chip (ldo6ajsa)
2022-09-06 | 8:45 | 16:15 | worked on schematic, helped students via meeting, started power management system design, tried to test stepper motor driver
2022-09-07 | 9:20 | 16:30 | Worked on schematic, found regulators, threw schematic away that i just created, found new regulator and started new design. Had a talk with Jeroen about my funcionality and gave me tips, feedback and tops. Also did some research on EMC/EMI
2022-09-08 | 9:00 | 16:30 | Worked on schematic, started heating and cooling design, updated a lot of designs and talked with jeroen.
2022-09-09 | 10:00 | 15:00 | found a H-bridge for peltier module and integrated it in the schematic, worked on the documentation (choices etc)
2022-09-12 | 8:45 | 16:00 | added labels to trello, added ESD circuit to i2c, tried to get tmc2208 to work: no succes. Helped students with their projects/questions and gathered emergency materials from Jelle. Created 5V PSU for breadboard
2022-09-13 | 9:00 | 16:45 | talked with Johan Korten about my diagrams and further actions. Prepared for meeting (drew global setting of HCL), meeting with HCL and requested. Called with Jelle about lab materials and prepared a plan to call with jelle and jeroen in the (near) future. Figured out how to add custom footprints to kicadV6. Fixed the snapeda desktop edition and fixed the Mouser SamacSys part / footprint downloaders integration with kicadv6. Added footprints to all components and started pcb template
2022-09-14 | 9:15 | 16:45 | worked on schematic, added rpi connector and tested A4988 stepper motor driver
2022-09-15 | 11:30 | 17:00 | New approach tested (shorter work time, more productivity?), Improved schematic, included data from Jeroen's stepper setup. Talked with jeroen about project, software progress.
2022-09-16 | X | X | X
2022-09-19 | 9:30 | 15:00 | Finished schematic (ready for big review), installed piqt in pycharm, talked with S3 project groups about their proces. Made a knob in pyqt that controls RPI hardware PWM pin.
2022-09-20 | 9:30 | 15:00 | Tidied up component boxes and sorted components for extra efficiency and component ESD safety. Attended workshop (20 min), enh connectors schematic. Read trough S6 project's code.
2022-09-21 | 9:45 | 17:00 | Set-up raspberry pi remote connect (SSH) with VSC and github. Tested LED software remotely on pi. Got QTPY knob working via ssh (PYQT5) conversation with Jeroen about pcb, schematic, software development and testing
2022-09-22 | 10:00 | 17:00 | Fixed schematic V1.0 by using all the notes that jeroen has created on that version. Found new parts and attended interview at the fablab.
2022-09-23 | 11:30 | 15:00 | gained more info on pyqt slots and signals. Bought a book on pyqt5, read it for a part and practised design skills
2022-09-26 | 9:30 |  | Read in the pyqt book, tried sliders and knobs and ticks etc. added phoenix ptsm connectors to schematic