## Tabelle1
Datum | Starttijd | Eindtijd | Bezigheden
2022-08-24 | 10:00 | 13:00 | Intro conversation with Jeroen Veen
2022-08-29 | 9:00 | 14:00 | kickoff + worked on POA
2022-08-30 | 9:15 | 15:00 | Worked on POA, conversation with jeroen about product functionality, details
2022-08-31 | 11:00 | 16:00 | Worked on global design, kesselring methode, conversation jeroen about global design.
2022-09-01 | 9:00 | 17:00 | Pros and cons list created. State diagram created. Systeem architectuur enhanced after conversation with jeroen
2022-09-02 | 10:00 | 16:30 | Worked on schematic for led, tested led, read datasheet led and led-driver
2022-09-05 | 9:00 | 16:00 | Worked on schematic for led with new chip, solderd cn5711 driver for led for testing, back-upped old and created fresh raspberry pi image. Wrote hardware pwm code python for cn5711 chip (ldo6ajsa)
2022-09-06 | 8:45 | 16:15 | worked on schematic, helped students via meeting, started power management system design, tried to test stepper motor driver
2022-09-07 | 9:20 | 16:30 | Worked on schematic, found regulators, threw schematic away that i just created, found new regulator and started new design. Had a talk with Jeroen about my funcionality and gave me tips, feedback and tops. Also did some research on EMC/EMI
2022-09-08 | 9:00 | 16:30 | Worked on schematic, started heating and cooling design, updated a lot of designs and talked with jeroen.
2022-09-09 | 10:00 | 15:00 | found a H-bridge for peltier module and integrated it in the schematic, worked on the documentation (choices etc)
2022-09-12 | 8:45 | 16:00 | added labels to trello, added ESD circuit to i2c, tried to get tmc2208 to work: no succes. Helped students with their projects/questions and gathered emergency materials from Jelle. Created 5V PSU for breadboard
2022-09-13 | 9:00 | 16:45 | talked with Johan Korten about my diagrams and further actions. Prepared for meeting (drew global setting of HCL), meeting with HCL and requested. Called with Jelle about lab materials and prepared a plan to call with jelle and jeroen in the (near) future. Figured out how to add custom footprints to kicadV6. Fixed the snapeda desktop edition and fixed the Mouser SamacSys part / footprint downloaders integration with kicadv6. Added footprints to all components and started pcb template
2022-09-14 | 9:15 | 16:45 | worked on schematic, added rpi connector and tested A4988 stepper motor driver
2022-09-15 | 11:30 | 17:00 | New approach tested (shorter work time, more productivity?), Improved schematic, included data from Jeroen's stepper setup. Talked with jeroen about project, software progress.
2022-09-16 | X | X | X
2022-09-19 | 9:30 | 15:00 | Finished schematic (ready for big review), installed piqt in pycharm, talked with S3 project groups about their proces. Made a knob in pyqt that controls RPI hardware PWM pin.
2022-09-20 | 9:30 | 15:00 | Tidied up component boxes and sorted components for extra efficiency and component ESD safety. Attended workshop (20 min), enh connectors schematic. Read trough S6 project's code.
2022-09-21 | 9:45 | 17:00 | Set-up raspberry pi remote connect (SSH) with VSC and github. Tested LED software remotely on pi. Got QTPY knob working via ssh (PYQT5) conversation with Jeroen about pcb, schematic, software development and testing
2022-09-22 | 10:00 | 17:00 | Fixed schematic V1.0 by using all the notes that jeroen has created on that version. Found new parts and attended interview at the fablab.
2022-09-23 | 11:30 | 15:00 | gained more info on pyqt slots and signals. Bought a book on pyqt5, read it for a part and practised design skills
2022-09-26 | 9:30 | 17:00 | Read in the pyqt book, tried sliders and knobs and ticks etc. added phoenix ptsm connectors to schematic. Created GUI concept in draw.io for a better understanding of what to create
2022-09-27 | 10:00 | 17:00 | Python code for tmc2209 writen. Schematic enhanced and sent to johan brussen. Helped S3 students.
2022-09-28 | 9:15 | 16:45 | worked on GUI. Read the pyqt5 book. Got a working A4498 stepper motor setup. Read on OOP with python.
2022-09-29 | 10:00 | 16:00 | python stepper motor working, made test report, talked with johan brussen about schematic. Cleanup up kicad (libraries where bad)
2022-09-30 | x | x | x
2022-10-03 | 9:45 | 16:00 | watched and learned from videos on python OOP. Tried to create main window, but required data from jeroen. Expirimented with kicad export functionality.
2022-10-04 | 10:15 | 15:00 | started learning python with new book, worked on PCB footprints and lcsc part list
2022-10-05 | 10:00 | 13:00 | Worked on PCB footprints and added 3d models
2022-10-06 | x | x | x
2022-10-07 | 10:30 | 14:00 | Worked on pcb layout, improved pcb workflow skills (to prevent wasting time)
2022-10-10 | 9:20 | 16:00 | Worked on software architecture, with the help of Jan. Created new PCB layout (grouped components together)
2022-10-11 | 8:00 | 15:45 | Worked on pcb layout. Long meeting with jeroen and rudie and johan k.
2022-10-12 | 9:20 | 17:00 | explained why to choose PHOENIX instead of JST. Added connectors to pcb. Searched for better components
2022-10-13 | 8:40 | 16:00 | Studied using udemy python course
2022-10-17 | 9:15 | 14:30 | Studied using udemy python course, started and finished routing PCB. (I was ill this day)
2022-10-18 | x | x | Sick
2022-10-19 | x | x | Sick
2022-10-20 | 10:00 | 16:00 | worked on pcb, talked with johan b about pcb, talked with johan k on software design
2022-10-21 | 11:50 | 12:30 | worked on pcb trace thickness
2022-10-31 | 9:30 | 16:00 | worked on PPT presentation for Thursday and enlarged pcb traces (for power). Finished V0.1 of pcb (except for logo maybe)
2022-11-01 | 9:00 | 17:00 | Communicated with Jan on software, how to approach classes etc. Talked with jeroen -> finished PCB order, PCB's are done for now. Went on a programming spree, wrote classes and unit tests