## Tabelle1
Datum | Starttijd | Eindtijd | Bezigheden
2022-08-24 | 10:00 | 13:00 | Intro gesprek met Jeroen
2022-08-29 | 9:00 | 14:00 | kickoff + gewerkt aan POA
2022-08-30 | 9:15 | 15:00 | gewerkt POA, gesprek met jeroen product functionaliteit, uitwerkingen
2022-08-31 | 11:00 | 16:00 | gewerkt aan globaal ontwerp, kesselring overweging, gesprek met jeroen globaal ontwerp.
2022-09-01 | 9:00 | 17:00 | gewerkt aan pro's en con's lijst opzetje. State diagram gemaakt. Systeem architectuur aangepast na gesprek met Jeroen.
2022-09-02 | 10:00 | 16:30 | Worked on schematic for led, tested led, read datasheet led and led-driver
2022-09-05 | 9:00 | 16:00 | Worked on schematic for led with new chip, solderd cn5711 driver for led for testing, back-upped old and created fresh raspberry pi image. Wrote hardware pwm code python for cn5711 chip (ldo6ajsa)
2022-09-06 | 8:45 | 16:15 | worked on schematic, helped students via meeting, started power management system design, tried to test stepper motor driver
2022-09-07 | 9:20 | 16:30 | Worked on schematic, found regulators, threw schematic away that i just created, found new regulator and started new design. Had a talk with Jeroen about my funcionality and gave me tips, feedback and tops. Also did some research on EMC/EMI
2022-09-08 | 9:00 | 16:30 | Worked on schematic, started heating and cooling design, updated a lot of designs and talked with jeroen.
2022-09-09 | 10:00 | 15:00 | found a H-bridge for peltier module and integrated it in the schematic, worked on the documentation (choices etc)
2022-09-12 | 8:45 |  | added labels to trello (absolutely necessary)